## Sheet1
Methodology Decision Tool
click in a boxed-cell below to rate the aspect according to the mode descriptors, for each rating, enter from 0 to 10. A coloured bar will be shown to reflect the value.
[6 empty] | these are calculated | This compares modality, and indicates a preference, though outliers below must be addressed
| "Ready. Aim. Aim. Fire." |  |  | "Aim-fire, aim-fire… Ready." |  | 1 Mode 2
Aspect | Considering Mode 1 (Waterfall) |  |  | Considering Mode 2 (Agile) |  | -3.3
Business Process is… | known and predictable, core business (maybe minor LEAN work) |  |  | unknown or being significantly (re-) designed
| 2 |  | 1.1 | 3 | 1.3 | 0.7 | small-number weightings are relative to other aspects in the vertical (mode)
Team Preferences are… | methodical, deliberate, risk-averse, "correct" is important, prescriptive |  |  | active and constant collaboration, embracing the unknown, comfortable with risk and failure, deliver quickly, ok with ad-hoc
| 4 |  | 1.6 | 2 | 1.5 | -2.8
Resources are… | traditional resources with traditional skills, or very new to agile |  |  | very comfortable with the agile experience
| 6 |  | 1.6 | 3 | 1.6 | -4.8
Technology & Toolset is… | “institutional”, legacy, predictable, familiar, hardware |  |  | innovative; built for collaboration & community; open, cloud
| 1 |  | 1.5 | 3 | 1.4 | 3.1
Implementation Algorithm… | is known, predictable, sequential |  |  | will require significant experimentation and discovery
| 2 |  | 1.4 | 3 | 1.5 | 1.7
Delivery Platform is… | predominantly server-side |  |  | mainly mobile
| 3 |  | 1 | 3 | 1.7 | 2.1
The product is… | a system of record, critical, or a document |  |  | innovative, leading- or bleeding-edge, or organisational
| 6 |  | 1.3 | 3 | 1.5 | -3.3
| 33.3 |  |  | 30
| Mode 1 potential |  |  | Mode 2 potential
These "potential" indicators are simple totals of weighted aspects, and show the potential viability of each approach.